## February
eCase Update Schedule
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 6 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
CEST | 8 | 10 | 8 | 0 | 25%
FDC | 8 | 10 | 8 | 0 | 25%
Heinz | 8 | 10 | 8 | 0 | 25%
Millstone | 9 | 11 | 0 | 0 | 0%
Cornblatt | 9 | 11 | 0 | 0 | 0%
Feinstein | 10 | 12 | 0 | 0 | 0%
Richards | 10 | 12 | 0 | 0 | 0%
VA Exams | 11 | 13 | 0 | 0 | 0%
VA Medical opinions | 11 | 13 | 0 | 0 | 0%
Richards | 14 | 16 | 0 | 0 | 0%
Collins | 14 | 16 | 0 | 0 | 0%
Andrews | 15 | 17 | 0 | 0 | 0%
Johnson | 16 | 17 | 0 | 0 | 0%
McDillard | 17 | 21 | 0 | 0 | 0%
Non-Original | 16 | 21 | 0 | 0 | 0%
Herbicides | 17 | 22 | 0 | 0 | 0%
Barrett | 21 | 22 | 0 | 0 | 0%
Baxter | 22 | 24 | 0 | 0 | 0%
Collins-SubDev | 22 | 24 | 0 | 0 | 0%
Cornblatt-SubDev | 23 | 23 | 0 | 0 | 0%
Ludlum | 23 | 25 | 0 | 0 | 0%
PTSD | 21 | 23 | 0 | 0 | 0%
SubDev | 21 | 23 | 0 | 0 | 0%
Activity 24 | 0 | 5 | 0 | 0 | 0%
Activity 25 | 0 | 5 | 0 | 0 | 0%
Activity 26 | 0 | 0 | 0 | 0 | 0%

## March
eCase Update Schedule
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 6 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
CEST | 8 | 10 | 8 | 0 | 25%
FDC | 8 | 10 | 8 | 0 | 25%
Heinz | 8 | 10 | 0 | 0 | 0%
Millstone | 9 | 11 | 0 | 0 | 0%
Cornblatt | 9 | 11 | 0 | 0 | 0%
Feinstein | 10 | 12 | 0 | 0 | 0%
Richards | 10 | 12 | 0 | 0 | 0%
VA Exams | 11 | 13 | 0 | 0 | 0%
VA Medical opinions | 11 | 13 | 0 | 0 | 0%
Richards | 14 | 16 | 0 | 0 | 0%
Collins | 14 | 16 | 0 | 0 | 0%
Andrews | 15 | 17 | 0 | 0 | 0%
Johnson | 16 | 17 | 0 | 0 | 0%
McDillard | 17 | 21 | 0 | 0 | 0%
Non-Original | 16 | 21 | 0 | 0 | 0%
Herbicides | 17 | 22 | 0 | 0 | 0%
Barrett | 21 | 22 | 0 | 0 | 0%
Baxter | 22 | 24 | 0 | 0 | 0%
Collins-SubDev | 22 | 24 | 0 | 0 | 0%
Cornblatt-SubDev | 23 | 23 | 0 | 0 | 0%
Ludlum | 23 | 25 | 0 | 0 | 0%
PTSD | 21 | 23 | 0 | 0 | 0%
SubDev | 21 | 23 | 0 | 0 | 0%
Activity 24 | 0 | 5 | 0 | 0 | 0%
Activity 25 | 0 | 5 | 0 | 0 | 0%
Activity 26 | 0 | 0 | 0 | 0 | 0%

## April
eCase Update Schedule
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 6 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
CEST | 8 | 10 | 8 | 0 | 25%
FDC | 8 | 10 | 8 | 0 | 25%
Heinz | 8 | 10 | 0 | 0 | 0%
Millstone | 9 | 11 | 0 | 0 | 0%
Cornblatt | 9 | 11 | 0 | 0 | 0%
Feinstein | 10 | 12 | 0 | 0 | 0%
Richards | 10 | 12 | 0 | 0 | 0%
VA Exams | 11 | 13 | 0 | 0 | 0%
VA Medical opinions | 11 | 13 | 0 | 0 | 0%
Richards | 14 | 16 | 0 | 0 | 0%
Collins | 14 | 16 | 0 | 0 | 0%
Andrews | 15 | 17 | 0 | 0 | 0%
Johnson | 16 | 17 | 0 | 0 | 0%
McDillard | 17 | 21 | 0 | 0 | 0%
Non-Original | 16 | 21 | 0 | 0 | 0%
Herbicides | 17 | 22 | 0 | 0 | 0%
Barrett | 21 | 22 | 0 | 0 | 0%
Baxter | 22 | 24 | 0 | 0 | 0%
Collins-SubDev | 22 | 24 | 0 | 0 | 0%
Cornblatt-SubDev | 23 | 23 | 0 | 0 | 0%
Ludlum | 23 | 25 | 0 | 0 | 0%
PTSD | 21 | 23 | 0 | 0 | 0%
SubDev | 21 | 23 | 0 | 0 | 0%
Activity 24 | 0 | 5 | 0 | 0 | 0%
Activity 25 | 0 | 5 | 0 | 0 | 0%
Activity 26 | 0 | 0 | 0 | 0 | 0%

## May
eCase Update Schedule
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 6 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
CEST | 8 | 10 | 8 | 0 | 25%
FDC | 8 | 10 | 8 | 0 | 25%
Heinz | 8 | 10 | 0 | 0 | 0%
Millstone | 9 | 11 | 0 | 0 | 0%
Cornblatt | 9 | 11 | 0 | 0 | 0%
Feinstein | 10 | 12 | 0 | 0 | 0%
Richards | 10 | 12 | 0 | 0 | 0%
VA Exams | 11 | 13 | 0 | 0 | 0%
VA Medical opinions | 11 | 13 | 0 | 0 | 0%
Richards | 14 | 16 | 0 | 0 | 0%
Collins | 14 | 16 | 0 | 0 | 0%
Andrews | 15 | 17 | 0 | 0 | 0%
Johnson | 16 | 17 | 0 | 0 | 0%
McDillard | 17 | 21 | 0 | 0 | 0%
Non-Original | 16 | 21 | 0 | 0 | 0%
Herbicides | 17 | 22 | 0 | 0 | 0%
Barrett | 21 | 22 | 0 | 0 | 0%
Baxter | 22 | 24 | 0 | 0 | 0%
Collins-SubDev | 22 | 24 | 0 | 0 | 0%
Cornblatt-SubDev | 23 | 23 | 0 | 0 | 0%
Ludlum | 23 | 25 | 0 | 0 | 0%
PTSD | 21 | 23 | 0 | 0 | 0%
SubDev | 21 | 23 | 0 | 0 | 0%
Activity 24 | 0 | 5 | 0 | 0 | 0%
Activity 25 | 0 | 5 | 0 | 0 | 0%
Activity 26 | 0 | 0 | 0 | 0 | 0%

## June
eCase Update Schedule
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 6 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
CEST | 8 | 10 | 8 | 0 | 25%
FDC | 8 | 10 | 8 | 0 | 25%
Heinz | 8 | 10 | 0 | 0 | 0%
Millstone | 9 | 11 | 0 | 0 | 0%
Cornblatt | 9 | 11 | 0 | 0 | 0%
Feinstein | 10 | 12 | 0 | 0 | 0%
Richards | 10 | 12 | 0 | 0 | 0%
VA Exams | 11 | 13 | 0 | 0 | 0%
VA Medical opinions | 11 | 13 | 0 | 0 | 0%
Richards | 14 | 16 | 0 | 0 | 0%
Collins | 14 | 16 | 0 | 0 | 0%
Andrews | 15 | 17 | 0 | 0 | 0%
Johnson | 16 | 17 | 0 | 0 | 0%
McDillard | 17 | 21 | 0 | 0 | 0%
Non-Original | 16 | 21 | 0 | 0 | 0%
Herbicides | 17 | 22 | 0 | 0 | 0%
Barrett | 21 | 22 | 0 | 0 | 0%
Baxter | 22 | 24 | 0 | 0 | 0%
Collins-SubDev | 22 | 24 | 0 | 0 | 0%
Cornblatt-SubDev | 23 | 23 | 0 | 0 | 0%
Ludlum | 23 | 25 | 0 | 0 | 0%
PTSD | 21 | 23 | 0 | 0 | 0%
SubDev | 21 | 23 | 0 | 0 | 0%
Activity 24 | 0 | 5 | 0 | 0 | 0%
Activity 25 | 0 | 5 | 0 | 0 | 0%
Activity 26 | 0 | 0 | 0 | 0 | 0%

## July
eCase Update Schedule
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 6 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
CEST | 8 | 10 | 8 | 0 | 25%
FDC | 8 | 10 | 8 | 0 | 25%
Heinz | 8 | 10 | 0 | 0 | 0%
Millstone | 9 | 11 | 0 | 0 | 0%
Cornblatt | 9 | 11 | 0 | 0 | 0%
Feinstein | 10 | 12 | 0 | 0 | 0%
Richards | 10 | 12 | 0 | 0 | 0%
VA Exams | 11 | 13 | 0 | 0 | 0%
VA Medical opinions | 11 | 13 | 0 | 0 | 0%
Richards | 14 | 16 | 0 | 0 | 0%
Collins | 14 | 16 | 0 | 0 | 0%
Andrews | 15 | 17 | 0 | 0 | 0%
Johnson | 16 | 17 | 0 | 0 | 0%
McDillard | 17 | 21 | 0 | 0 | 0%
Non-Original | 16 | 21 | 0 | 0 | 0%
Herbicides | 17 | 22 | 0 | 0 | 0%
Barrett | 21 | 22 | 0 | 0 | 0%
Baxter | 22 | 24 | 0 | 0 | 0%
Collins-SubDev | 22 | 24 | 0 | 0 | 0%
Cornblatt-SubDev | 23 | 23 | 0 | 0 | 0%
Ludlum | 23 | 25 | 0 | 0 | 0%
PTSD | 21 | 23 | 0 | 0 | 0%
SubDev | 21 | 23 | 0 | 0 | 0%
Activity 24 | 0 | 5 | 0 | 0 | 0%
Activity 25 | 0 | 5 | 0 | 0 | 0%
Activity 26 | 0 | 0 | 0 | 0 | 0%